## Sheet1
Sr.No | Date | Requirements | AMC/Non-AMC | Implement Type | Man Hours | Completion Status | Completion % | Completed On | Charges Per Hour | Calculated Amount | Amount Receivd on 23-Mar-2023 | 40500 | For completing Pending Issues
1 | 2023-03-03 | SMS Integration | AMC Paid | Bug Fix | 30 | Completed | 100% | 2023-03-25 | 0 | 0
2 | 2023-03-25 | Bill Number Reset | AMC Paid | Add-On | 4 | Completed | 100% | 2023-04-01 | 0 | 0
3 | 2023-03-25 | Total Mismatch Issue | AMC Paid | Bug Fix | 1 | Completed | 100% | 2023-03-25 | 0 | 0
4 | 2023-04-04 | Total Mismatch Issue | AMC Paid | Bug Fix | 1 | Completed | 100% | 2023-04-06 | 0 | 0
5 | 2023-04-10 | Total Mismatch Issue | AMC Paid | Bug Fix | 1 | Completed | 100% | 2023-04-12 | 0 | 0
6 | 2023-04-10 | Club Email, WebSite, Waiter Name should be print in Bill | Not Paid | Add-On | 5 | Completed | 100% | 2023-08-30 | 600 | 3000
7 | 2023-04-24 | Update Membership Number | Not Paid | Add-On | 6 | Completed | 100% | 2023-08-30 | 600 | 3600
8 | 2023-04-10 | Add Member Type in Member Creation | Not Paid | Enhancement | 4 | Completed | 100% | 2023-08-30 | 600 | 2400
9 | 2023-04-10 | Salutation in Member Creation Form | Not Paid | Enhancement | 4 | Completed | 100% | 2023-08-30 | 600 | 2400
10 | 2023-09-09 | Update Membership Type and Salutation in Database | Not Paid | Enhancement | 1 | Completed | 100% | 2023-09-09 | 600 | 600
11 | 2023-04-10 | Service Report - Category Wise | Not Paid | Enhancement | 6 | In-Progress | 30% |  | 600 | 3600
12 | 2023-04-10 | Member Type Report - Category Wise | Not Paid | Enhancement | 4 | In-Progress | 30% |  | 600 | 2400
13 | 2023-04-10 | Guest Bill Report | Not Paid | Enhancement | 6 | In-Progress | 30% |  | 600 | 3600
14 | 2023-09-02 | Adding Member Photo in Member Form | Not Paid | Enhancement | 3 | Yet to Start |  |  | 600 | 1800
15 | 2023-09-02 | Adding Member Documents in Member Form | Not Paid | Enhancement | 3 | Yet to Start |  |  | 600 | 1800
16 | 2023-09-02 | Adding Member History in Member Form (Date, Comments, Upload Image / PDF / Videos) | Not Paid | Enhancement | 10 | Yet to Start |  |  | 600 | 6000
17 | 2023-09-02 | Member Report with History | Not Paid | Enhancement | 10 | Yet to Start |  |  | 600 | 6000
18 | 2023-09-02 | Dropdown Waiter Name in Liquor Order Page | Not Paid | Enhancement | 3 | Yet to Start |  |  | 600 | 1800
19 | 2023-09-07 | Sync the data between Primary and Secondary server | Not Paid | Enhancement | 8 | Yet to Start |  |  | 600 | 4800

## Sheet2
Sr.No | Requested Date | Requirements | Man Hours | Completion Status | Completed On | Charges Per Hour | Estimated Amount | Billed Amount
1 | 2023-04-10 | Club Email, WebSite, Waiter Name should be print in Bill | 5 | Completed | 2023-08-30 | 600 | 3000 | 3000
2 | 2023-04-10 | Add Member Type in Member Creation | 4 | Completed | 2023-08-30 | 600 | 2400 | 2400
3 | 2023-04-10 | Salutation in Member Creation Form | 4 | Completed | 2023-08-30 | 600 | 2400 | 2400
4 | 2023-04-10 | Service Report - Category Wise | 6 | Yet to Start |  | 600 | 3600 | 0
5 | 2023-04-10 | Member Type Report - Category Wise | 4 | Yet to Start |  | 600 | 2400 | 0
6 | 2023-04-10 | Guest Bill Report | 6 | Yet to Start |  | 600 | 3600 | 0
7 | 2023-04-24 | Update Membership Number | 6 | Completed | 2023-08-30 | 600 | 3600 | 3600
8 | 2023-09-02 | Adding Member Photo in Member Form | 4 | Completed | 2023-09-12 | 600 | 2400 | 2400
9 | 2023-09-02 | Adding Member History in Member Form (Date, Comments, Upload Image / PDF / Videos) | 10 | Yet to Start |  | 600 | 6000 | 0
10 | 2023-09-02 | Member Report with History | 10 | Yet to Start |  | 600 | 6000 | 0
11 | 2023-09-02 | Dropdown Waiter Name in Liquor Order Page | 3 | Yet to Start |  | 600 | 1800 | 0
12 | 2023-09-07 | Sync the data between Primary and Secondary server | 8 | Yet to Start |  | 600 | 4800 | 0
13 | 2023-09-07 | Room Booking Page | 8 | Yet to Start |  | 600 | 4800 | 0
14 | 2023-09-07 | Room Booking Report | 8 | Yet to Start |  | 600 | 4800 | 0
15 | 2023-09-09 | Update Membership Type and Salutation in Database | 1 | Completed | 2023-09-09 | 600 | 600 | 600
16 | 2023-09-09 | Load the pre-defined Waiter Names in Liquor Order Page and Implement Validation | 2 | Yet to Start |  | 600 | 1200 | 0
|  | Total Hours and Charges | 89 |  |  |  | 53400 | 14400