## Sheet2
Sr.No | Date | Requirements | Man Hours | Completion Status | Completed On | Charges Per Hour | Calculated Amount
1 | 2023-04-10 | Club Email, WebSite, Waiter Name should be print in Bill | 5 | Completed | 2023-08-30 | 600 | 3000
2 | 2023-04-24 | Update Membership Number | 6 | Completed | 2023-08-30 | 600 | 3600
3 | 2023-04-10 | Add Member Type in Member Creation | 4 | Completed | 2023-08-30 | 600 | 2400
4 | 2023-04-10 | Salutation in Member Creation Form | 4 | Completed | 2023-08-30 | 600 | 2400
5 | 2023-09-09 | Update Membership Type and Salutation in Database | 1 | Completed | 2023-09-09 | 600 | 600
6 | 2023-04-10 | Service Report - Category Wise | 6 | Yet to Start |  | 600 | 3600
7 | 2023-04-10 | Member Type Report - Category Wise | 4 | Yet to Start |  | 600 | 2400
8 | 2023-04-10 | Guest Bill Report | 6 | Yet to Start |  | 600 | 3600
9 | 2023-09-02 | Adding Member Photo in Member Form | 3 | Yet to Start |  | 600 | 1800
10 | 2023-09-02 | Adding Member Documents in Member Form | 3 | Yet to Start |  | 600 | 1800
11 | 2023-09-02 | Adding Member History in Member Form (Date, Comments, Upload Image / PDF / Videos) | 10 | Yet to Start |  | 600 | 6000
12 | 2023-09-02 | Member Report with History | 10 | Yet to Start |  | 600 | 6000
13 | 2023-09-02 | Dropdown Waiter Name in Liquor Order Page | 3 | Yet to Start |  | 600 | 1800
14 | 2023-09-07 | Sync the data between Primary and Secondary server | 8 | Yet to Start |  | 600 | 4800
|  | Total Hours and Charges | 73 |  |  |  | 43800