## Sheet1
Sr.No | Date | Requirements | AMC/Non-AMC | Implement Type | Man Hours | Completion Status | Completion % | Completed On | Charges Per Hour | Calculated Amount | Amount Receivd on 23-Mar-2023 | 40500 | For completing Pending Issues
1 | 2023-03-03 | SMS Integration | AMC Paid | Bug Fix | 30 | Completed | 100% | 2023-03-25 | 0 | 0
2 | 2023-03-25 | Bill Number Reset | AMC Paid | Add-On | 4 | Completed | 100% | 2023-04-01 | 0 | 0
3 | 2023-03-25 | Total Mismatch Issue | AMC Paid | Bug Fix | 1 | Completed | 100% | 2023-03-25 | 0 | 0
4 | 2023-04-04 | Total Mismatch Issue | AMC Paid | Bug Fix | 1 | Completed | 100% | 2023-04-06 | 0 | 0
5 | 2023-04-10 | Total Mismatch Issue | AMC Paid | Bug Fix | 1 | Completed | 100% | 2023-04-12 | 0 | 0
6 | 2023-04-10 | Club Email, WebSite, Waiter Name should be print in Bill | Not Paid | Add-On | 5 | Completed | 100% | 2023-08-30 | 600 | 3000
7 | 2023-04-24 | Update Membership Number | Not Paid | Add-On | 6 | Completed | 100% | 2023-08-30 | 600 | 3600
8 | 2023-04-10 | Service Report - Category Wise | Not Paid | Enhancement | 6 | In-Progress | 30% |  | 600 | 3600
9 | 2023-04-10 | Add Member Type in Member Creation | Not Paid | Enhancement | 4 | Completed | 100% | 2023-08-30 | 600 | 2400
10 | 2023-04-10 | Member Type Report - Category Wise | Not Paid | Enhancement | 4 | In-Progress | 30% |  | 600 | 2400
11 | 2023-04-10 | Salutation in Member Creation Form | Not Paid | Enhancement | 4 | Completed | 100% | 2023-08-30 | 600 | 2400
12 | 2023-04-10 | Guest Bill Report | Not Paid | Enhancement | 6 | In-Progress | 30% |  | 600 | 3600
[9 empty] | Total Amount | 21000